## GanttChart
The Lawrence Project: Project Schedule | [8 empty] | Gantt Chart Template © 2016 by Vertex42.com.
Team Liquid | [8 empty] | See info on Gantt Chart Template Pro
Project Lead:
| Project Start Date: |  |  | 2017-10-23 | time axis 2017-10-23 to 2017-12-18
| Display Week: |  |  | 1 |  |  |  |  | 2017-10-23: Week 1; 2017-10-30: Week 2; 2017-11-06: Week 3; 2017-11-13: Week 4; 2017-11-20: Week 5; 2017-11-27: Week 6; 2017-12-04: Week 7; 2017-12-11: Week 8
[9 empty] | 2017-10-23 | [6 empty] | 2017-10-30 | [6 empty] | 2017-11-06 | [6 empty] | 2017-11-13 | [6 empty] | 2017-11-20 | [6 empty] | 2017-11-27 | [6 empty] | 2017-12-04 | [6 empty] | 2017-12-11
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Project 3, Prototype
1.1 | Initial Design | Group |  | 2017-10-23 | 2017-10-26 | 4 | 100% | 4
1.2 | Implementation - Player | Chong |  | 2017-10-27 | 2017-10-29 | 3 | 100% | 3
1.3 | Implementation - Enemies | John |  | 2017-10-27 | 2017-10-29 | 3 | 100% | 3
1.4 | Implementation - Map | Lu |  | 2017-10-27 | 2017-10-29 | 3 | 100% | 3
1.5 | Integration of Parts | Group |  | 2017-10-30 | 2017-11-02 | 4 | 100% | 4
1.6 | Testing of Integration | Group |  | 2017-11-03 | 2017-11-05 | 3 | 100% | 3
2 | Modeling
2.1 | Design |  |  | 2017-11-12 | 2017-11-15 | 4 | 0% | 4
2.2 | Implementation |  |  | 2017-11-16 | 2017-11-22 | 7 | 0% | 7
2.3 | Integration |  |  | 2017-11-23 | 2017-11-25 | 3 | 0% | 3
2.4 | Testing |  |  | 2017-11-26 | 2017-11-27 | 2 | 0% | 2
3 | UI
3.1 | Design |  |  | 2017-11-06 | 2017-11-06 | 1 | 0% | 1
3.2 | Implementation |  |  | 2017-11-07 | 2017-11-09 | 3 | 0% | 3
3.3 | Integration |  |  | 2017-11-10 | 2017-11-11 | 2 | 0% | 2
3.4 | Testing |  |  | 2017-11-12 | 2017-11-12 | 1 | 0% | 1
4 | Attack Upgrades
4.1 | Design |  |  | 2017-11-06 | 2017-11-08 | 3 | 0% | 3
4.2 | Implementation |  |  | 2017-11-09 | 2017-11-13 | 5 | 0% | 5
4.3 | Integration |  |  | 2017-11-14 | 2017-11-14 | 1 | 0% | 1
4.4 | Testing |  |  | 2017-11-15 | 2017-11-16 | 2 | 0% | 2
5 | Enemy Health/Variations
5.1 | Design |  |  | 2017-11-06 | 2017-11-07 | 2 | 0% | 2
5.2 | Implementation |  |  | 2017-11-08 | 2017-11-09 | 2 | 0% | 2
5.3 | Integration |  |  | 2017-11-10 | 2017-11-10 | 1 | 0% | 1
5.4 | Testing |  |  | 2017-11-11 | 2017-11-11 | 1 | 0% | 1
6 | Base Health
6.1 | Design |  |  | 2017-11-13 | 2017-11-13 | 1 | 0% | 1
6.2 | Implementation |  |  | 2017-11-14 | 2017-11-14 | 1 | 0% | 1
6.3 | Integration |  |  | 2017-11-15 | 2017-11-15 | 1 | 0% | 1
6.4 | Testing |  |  | 2017-11-16 | 2017-11-16 | 1 | 0% | 1
7 | Turrets
7.1 | Design |  |  | 2017-11-28 | 2017-11-30 | 3 | 0% | 3
7.2 | Implementation |  |  | 2017-12-01 | 2017-12-04 | 4 | 0% | 4
7.3 | Integration |  |  | 2017-12-05 | 2017-12-06 | 2 | 0% | 2
7.4 | Testing |  |  | 2017-12-07 | 2017-12-08 | 2 | 0% | 2
8 | Multiple Lanes
8.1 | Design |  |  | 2017-11-17 | 2017-11-17 | 1 | 0% | 1
8.2 | Implementation |  |  | 2017-11-18 | 2017-11-18 | 1 | 0% | 1
8.3 | Integration |  |  | 2017-11-19 | 2017-11-19 | 1 | 0% | 1
8.4 | Testing |  |  | 2017-11-20 | 2017-11-20 | 1 | 0% | 1
9 | Testing | Group
9.1 | Final Testing and Optimization |  |  | 2017-12-09 | 2017-12-17 | 9 | 0% | 9
9.2 | Implementation |  |  | 2017-12-18 | 2017-12-18 | 1 | 0% | 1
9.3 | Integration |  |  | 2017-12-19 | 2017-12-19 | 1 | 0% | 1
9.4 | Testing |  |  | 2017-12-20 | 2017-12-20 | 1 | 0% | 1
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
CATEGORY ROWS and WBS NUMBERING
1 | [ Task Category (label only) ]
1.1 | [ Level 2 Task ]
1.1.1 | . [ Level 3 Task ]
1.1.1.1 | . . [ Level 4 Task ]
Examples of ways to define tasks
1 | [ Task Category (summary) ] |  |  | 2015-04-01 | 2015-04-17 | 17 |  | 13
2 | Milestone |  |  | 2015-04-01 | 2015-04-01 | 1 |  | 1
2.1 | [ Start Date and Calendar Days ] |  |  | 2015-04-01 | 2015-04-03 | 3 |  | 3
2.2 | [ Start the next day after another Task ] |  |  | 2015-04-04 | 2015-04-10 | 7 |  | 5
2.3 | [ Start next work day after another Task] |  |  | 2015-04-13 | 2015-04-17 | 5 |  | 5
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## GanttChartPro
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn More About Gantt Chart Template Pro
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Unlocked
The Pro version does not have password protected worksheets, so you can fully customize it
and add worksheets as needed, within the limits of the terms of use.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies,
the Pro version includes template rows that calculate the Start date based
on the WBS number that you enter in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The Pro version for Excel Online uses the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Learn More About Gantt Chart Template Pro

## Help
HELP
Version: Gantt Chart Template for Office 365 - FREE Version
Intro
This Gantt Chart spreadsheet is designed to to help you create a simple project schedule. You
only need to know some basic spreadsheet operations, such as how to insert, delete, copy and
and paste rows and cells. For more advanced uses, such as defining task dependencies, you
will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos on Vertex42.com
Before sharing this spreadsheet, please read the license agreement in the TermsOfUse worksheet.
Getting Started Tips
| - Input cells for defining the task dates and durations have a light green background. | Input Cell
- [ Bracketed Text ] is meant to be edited, like the project title and task descriptions.
| - Some of the labels include cell comments to provide extra help information. | Label
- The Project Start Date determines the first week shown in the gantt chart.
- To adjust the range of dates shown in the gantt chart, change the Display Week.
- To insert a new task, insert a new row, then copy/paste a row from the selection of template
rows at the bottom of the worksheet, depending on how you want to define the task.
- If you see "#####" in a cell, widen the column to display the cell contents.
- Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Using the Template Rows and Choosing a WBS Level
Inserting New Tasks.
1. Insert a new blank row where you want the new task to be.
2. Copy the entire row you want to use from the set of template rows.
3. Paste the row you copied on top of the new row you just inserted.
4. Copy and paste the WBS cell separately, based on the level (1, 1.2, 1.2.3, 1.2.3.4)
Important: When inserting new rows, you must copy and paste an entire row, because the cells of the Gantt chart area are formulas.
Changing the WBS Level in the WBS Column
- The WBS numbering uses a different formula for each level, but the formula does not reference any other cell in the row. So, you can copy and paste just the WBS cell that you want to use.
- If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter them if you need to.
- You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Category Tasks
- You can use tasks that are just labels, but it may be useful for a category task to display the minimum Start date and maximum End date of its sub tasks. This can be done using =MIN(range_of_startdates) and =MAX(range_of_enddates).
Creating Task Dependencies
- You can enter the Start date manually, or define task dependecies using a formula. Below are the most common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3 )+1
E. | Set the Start date to a number of days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
E. | Use the Predecessor column to start the day after another task
[ Template rows that use this feature are only in the PRO version ]
Changing the End Date Font to Red when Behind Schedule
[ This feature is only in the PRO version, but if you are familiar with conditional formatting, you could try doing this yourself. ]
Changing the Color of the Bars in the Gantt Chart
[ This feature is only in the PRO version. ]
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is one of the main features of the Pro version. If you want to figure it out on your own, use the WORKDAY() function to define the End Date and calculate the Calendar Days based on the Start and End dates.
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a category task can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: =SUMPRODUCT(H9:H15,J9:J15)/SUM(H9:H15)
Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area.
Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Marings, and
Page Orientation as desired.
Q: | The Start date, End date, or %Complete for a Level 1 task is wrong. How do I fix it?
When using =MIN(), =MAX(), and =SUMPRODUCT(), it is easy for the references to get messed up if you move rows around or insert new rows. You should verify and fix these formulas if they are not referencing the correct ranges.
Example: The image below shows that the MIN() function is not referencing all of the sub tasks.
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2015 Vertex42 LLC
Note on C19: This is an example comment.

## TermsOfUse
Gantt Chart Template
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
By Vertex42.com
© 2006-2015 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.